## Slide 1
European Green Fast Lanes
Roll-out Plan Wave 2
July 2017

## Slide 2: Contents
The EGFL programme
  Introduction
  Scope
  Objectives
Roll-out plan
  High-level roll-out plan
  Detailed roll-out plan
3. Appendix

## Slide 3: Introduction The EGFL programme is based on five core themes
Rationalizing EU trucking schedules by considering actual transit times, GHA capabilities, potential for spread delivery and peak volumes at the hub
Providing status updates of shipments to customers, e.g. in case of Late-show
Launching a compliance checker that verifies shipment documentation and proactively signals potential violations of customs requirements
Implementing a 100% weighing requirement of individual shipments at outstations; updating the air waybill accordingly
Redesign of the cargo acceptance process at outstations: new procedures for handling late-show, no-show shipments, status messaging and rebooking
Weighing
Status updates
Acceptance procedures
Trucking rationalization
Compliance checker

## Slide 4: Scope (1/2) EGFL focuses on the initial part of the flow of goods and information from shipper to consignee
Outstation
Shipper
Forwarder
Consignee
Forwarder
Outstation
Hub (AMS/CDG)

## Slide 5: Scope (2/2) IATA-led industry group CargoIQ has defined air cargo milestones, which the EGFL programme follows
Hub (AMS/CDG)
Forwarder
Outstation
BKD = Capacity confirmed by carrier and Routemap generated
FWB = Freight Waybill (Electronic Air Waybill message) sent to carrier
LAT = Latest Acceptance Time
FOH = Freight On Hand message sent to forwarder upon warehouse receipt (message to Forwarder)
RCS = Cargo and documents received from shipper by GHA, 'Ready For Carriage‘ (message to Forwarder)
DEP = Departed at Outstation / Origin airport
ARR = Arrival at Hub
RCF = Cargo and Air Waybill have been received at final destination, ‘Ready for Carriage’
DEP*
FWB
ARR
= General CargoIQ indicator
= EGFL Performance Milestone
RCF
RCS
DEP
BKD
FOH
LAT
*This KPI is also highly dependent on external (airside) factors and hence not a fully representative indicator of programme success

## Slide 6: Objectives The main objectives of EGFL are to increase reliability and efficiency
Increase reliability (higher flown-as-planned) and reduce total transit time in order to provide a superior customer offering
  Increase aircraft load factor by effectively prioritizing cargo at the hub (‘hot’ or ‘not’). The focus is on optimizing flights rather than trucks.
1
3
2
  Achieve cost savings and enable future volume growth under given capacity restrictions by reducing repair, rework, and peak workload levels at the hub as well as at outstations
4
The EGFL programme aims to:
  Enhance collaboration and information sharing throughout the supply chain
5
  Enable proactive customs handling and increase customs compliance

## Slide 7: Contents
The EGFL programme
  Introduction
  Scope
  Objectives
Roll-out plan
  High-level roll-out plan
  Detailed roll-out plan
    General
    Swissport
3. Appendix

## Slide 8: High-level roll-out plan The roll-out per station can be divided into an initial onboarding stage, the actual roll-out and an ongoing communications and change stage
II.
Onboarding
III.
Roll-out
I.
Communications & change
Monitoring points
6w
6w
6w
6w
x w
Go-Live

## Slide 9: High-level roll-out plan Through the communications and change stream, continuous alignment of all stakeholders is warranted
I.
Communications & change
Internal
Create buy-in and alignment with Network Planning, Revenue Management and local AFKL Cargo representatives
Promote the benefits of the EGFL programme internally
Validate the new trucking schedule with Network Planning
Inform internal stakeholders about process changes after implementation of EGFL
Continuous monitoring after implementation
External
Create buy-in and alignment with customers, the GHA and truckers
Promote the benefits of the EGFL programme externally
Launch a customer newsletter to inform customers on EGFL and related changes
Conitnuous monitoring and alignment with the GHA and truckers
Monitor performance both during and after the 8-week implementation phase

## Slide 10: High-level roll-out plan During the onboarding phase, all stakeholders at the station are informed of the forthcoming implementation in order to drive buy-in and create alignment
Set up key parameters
During the preparation phase of 4 weeks, the new trucking schedule is first reviewed and finalized. Then, the trucking schedule is loaded in the NP and GHA systems to be ready for Go-Live on Tuesday in Week 3. System setup should therefore be completed by the end of Friday in Week 1.
Implement core processes
Perform an assessment of day-to-day operations at the GHA in the current situation to assess the change impact to come. Also verify the potential for Direct Pick-ups from customers in the area around this station.
Supporting activities
Review the existing ‘paperwork’: both contracts with the GHA and truckers as well as the local conditions that apply for customers in the region. Align with relevant internal (i.e. CSO, Kay Account Managers, Procurement) and external stakeholders. Timely adapt these documents so that they are compatible with EGFL requirements before Go-Live.
II.
Onboarding

## Slide 11: High-level roll-out plan During the roll-out phase, a station mini-assessment is conducted, the new processes are implemented and progress is monitored
III.
Roll-out
Implement core processes
After the trucking schedule is checked, validated and loaded into NP systems, the Go-Live will take place on Tuesday in Week 3. From this moment on, the new core acceptance processes related to EGFL should be carried out by the GHA as specified in the process descriptions
Implement ‘add-on’ processes
In addition to the core processes, several additional ‘add-on’ processes should be implemented, such as Selective Loading Rules, Weighing and Measuring, Direct Pick-up and the Compliance Checker. This does not necessarily have to happen immediately upon Go-Live, but can be done gradually during the weeks after.
Supporting activities
The performance improvements of the new operational trucking schedule and the acceptance processes should be measured, from the % of successful deliveries before LAT at the outstation to the % of Flown As Planned shipments leaving AMS (DEP AMS). If (quantified) performance falls behind expectations, corrective actions should be taken.

## Slide 12: Detailed roll-out plan The standard roll-out plan for each station distinguishes 5 clusters of activities stretching 8 weeks, which are preceded by 4 weeks of preparation
51
0
1
2
3
4
5
6
7
8
Make preparations to enable start of weighing in week 5
Test and resolve issues
3.3 Compliance Checker
3.2 Weighing
Test and resolve issues
1.2 Implement new trucking schedule
4.3 Set up KPI structure and monitor performance
3.1 Selective Loading Rules
2.2 Implement new acceptance processes
1.1 Create and review schedule
4.2 Review local conditions
2.1 Assess current acceptance process
4.1 Review local contract/SLA
5a. Ensure ongoing communication with local AFKL, Network Planning and RM
5b. Ensure ongoing communication with customers, GHA and Truckers
4. Supporting
activities
3. Implement
‘add-on’ processes
Local
AFKL
visit
2. Implement
core processes
1. Set up
key parameters
GHA
visit
Activity
Weekly presence at outstation
5. Communications
and change
Report-out
GO-LIVE
Week
Preparation Phase
Preparation (4 weeks)

## Slide 13: Detailed roll-out plan 1.1 Review trucking schedule
Review and finalize the newly made trucking schedule to ensure that the schedule is ultimately viable
1.1 Create and validate new trucking schedule
Create and validate the new truck schedule to verify its suitability and validate with GHA and local AFKL. This starts by defining feasible transit times (based on actual transit times), considering GHA opening hours, peaks of incoming cargo at the hub (mainly from 02:00 to 04:00 on Saturdays and Sundays) and reviewing the impact on blocks of connecting flights; have this discussion first with the FJ, and also with GHA, NP, local operations and CSO. Make sure that NP is aware of any changes (e.g. co-load options).
Use a single file with the same template on the Dropbox to enter the schedules. This makes the job easier for NP.
If multiple truckers are contracted: assign truckers to the trucking schedule (based on their current performance); which trucker is responsible for the booking trucks, and which for the others?
Ensure that, when NP starts using the schedule, it also contains relevant information on when (final) plannings have to be sent, and when FBL’s are sent. This enables NP to run a smooth process.
What and why?
Actions
When making the schedule, find a balance between what the market wants and what is practical/economical. For example in FLR, we started with one booking truck too many, which is expensive as it was often not full.
LAT is typically three hours before DEP, but this may still change depending on local circumstances. Be sensitive to what the local context requires!
Take good notice of the current trucking schedule and the new trucking schedule, to identify how strong the change for the station will ultimately be

## Slide 14: Detailed roll-out plan 1.2 Implement new trucking schedule
Coordinate the timely loading of the new trucking schedule into the systems (e.g. AFLS) to ensure that the schedule is operational on the Go-Live date
1.2 Implement new trucking schedule
What and why?
Schedule Go-Live on a suitable date. Tuesdays typically have low volumes, which allows you to have a smooth start towards peak volumes on Friday/Saturday. It also allows you to fly in on Monday and prepare. Other dates are also possible.
Notify Network Planning of the Go-Live date, and oversee that the validated trucking schedule is loaded into the systems of NP and the GHA, at least 10 days before Go-Live (i.e. end of Friday of week 1). During this 10-day transition period, NP works with both old and new schedules.
Involve BlueLink in the roll-out and inform of upcoming changes. Discuss with Patrick Voorbij.
Actions
It is critical that one, identical trucking schedule is loaded in the NP and GHA systems. Deviations between loaded schedules have earlier caused signficicant problems
After Go-Live, you will face resistance from local stakeholders or from AFKL commercial. This is a major pitfall and potential inhibitor to the success of the programme. Be prepared to identify these issues and deal with them. Seek support from e.g. Simon or the FJ’s.
Changes in the schedule after Go-Live are possible if the new situation requires it, but cannot happen too often as this will frustrate NP’s process.
10 days
Onboarding
Roll-out
Go-Live

## Slide 15: Detailed roll-out plan 2.1 Assess current acceptance process and ensure preparations are made
Assess and map day-to-day challenges and behavior, available resources (personnel, equipment). This gives an idea of the intensity of the change required and allows you to take actions in preparation for Go-Live
2.1 Assess acceptance process ensure preparations are made
What and why?
Make (at least) two visits before Go-Live: one to discuss EGFL with local AFKL and the GHA and to validate the trucking schedule, and another to become familiar with the GHA operations. This can also be during one trip.
  1. Visit the GHA and discuss with the AFKL Operations manager to discuss the EGFL programme and the impact it has, and to validate the trucking schedule. Also discuss IT (reporting) capabilities (for deviation and LAT reports), local acceptance procedures and behavior, as well as off-the-record agreements and ways of working established locally.
  2. Visit the GHA to get familiar with the GHA operation, and make an assessment of physically available resources (e.g. scanners, calibrated scales for weighing) that are needed for EGFL. The aim is to eventually enable weighing of 100% of shipments. If GHA resources are insufficient, this may require contractual changes (see 4.1).
Actions
Before implementation in FRA, it often happened that late deliveries were still loaded on their original trucks, as these trucks would wait for the shipments to be loaded. This is wrong, as it rewards the wrong customer behavior (i.e. late deliveries are still accepted and ‘fixed’) while we improve our own non-quality (we have less time at the hub).
Also, a lot of Go-Show shipments were simply sent from FRA to AMS without a booking. This is also something that needs to change in the context of EGFL.
4.1
Link to:

## Slide 16: Detailed roll-out plan 2.2 Implement new acceptance processes
Ensure that the EGFL acceptance processes are implemented and physically carried out as laid out in the process descriptions
2.2 Implement new acceptance processes
What and why?
At the GHA, oversee that Late-show, No-show, Go-show, Early-show and High-show processes are carried out correctly. This also entails that communication with e.g. NP, RM, CSO is well established, and that deviation reports are sent within 60 minutes after each truck departure. Refer to the EGFL process descriptions, flowcharts and GHA manual (Appendix). Checklist:
Actions
This step represents the actual, physical changes on the ground, starting directly after the Go-Live and system setup is finished (see 1.2).
Previous issues in this context (at FRA, CPH) have been a lack of available scanners
Another potential threat can be a lack of truck docks at the GHA, if volumes are high
Plan ahead regarding your visits to the station(s): which days are busy? When to fly there?
Good luck with declaring your expenses 
Forwarder arrival registration
Time registration in place (reporting)
Door management
Truckers informed about truck dock
Acceptance
All cargo is weighed, weighing receipts stored
Acceptance flows followed (see flowcharts, Appendix)
Documentation
RCS and FWB’ process followed correctly (see 3.2)
Customs
Role and impact mapped and integrated
After acceptance
Correct storage, build-up and planning
Interaction NP/Swissport
Line-truck ordering process in place
Pre-planning in place
GHA sends deviation reports to Network Planning
Line-haul driver process
Truck arrival reporting in place
Booking checks performed (ADR/COL/height/etc.)
Manifests / FFM Secure / DEP reporting in place
Departure registration (STM) in place

## Slide 17: Detailed roll-out plan 3.1 Selective Loading Rules
Oversee the adoption of Selective Loading Rules by the GHA, to ensure that ‘hot’ cargo is not mixed with ‘cold’ cargo, which will help the Hub operation
SLR
3.1 Selective Loading Rules
What and why?
Ideally, achieve that 4 (or 3/2 if less cargo is available) build up locations (buffers) are set up per truck in advance (see Appendix). This allows the incoming freight to be distributed as it arrives. Another method to demonstrate the selective loading principle is to use colored Post-It stickers (e.g. Blue, Green, Yellow and Red). Looking at the booking list, you can stick these to different shipments based on their ‘temperature’ in terms of remaining connection time at the hub. This way, the GHA can build up the correct pallets easily (blue with blue on one pallet, green with green on another, etc.). Normally, Network Planning has been sending over final planning with which the pallets were being built.
Actions
If Selective Loading Rules are not followed, ‘hot’ cargo will be loaded next to ‘cold’ cargo, meaning extra work at the Hub as they need to break down multiple plates to get to the ‘hot stuff’. By applying the selective loading rules, pressure is relieved from the Hub.
Link to:

## Slide 18: Detailed roll-out plan 3.2 Weighing
Realize the 100% weighing requirement of the EGFL programme, to improve insight in actual shipping volumes and to invoice actual weight to customers
2.1
Link to:
4.1
3.2 Weighing
What and why?
Make clear to the GHA and local AFKL what the benefit of weighing is. It will avoid the CCA process (e.g. additional charges sent to the customer after the cargo has been transported for exceeding the booked weight) as the corrected weight will be directly invoiced to the customer.
Oversee that 100% of cargo is weighed by the GHA. This implies that the GHA must have the required equipment and practices in place (see 2.1 and 4.1).
Instruct the GHA to create and store weighing receipts of all cargo and ensure that this is adhered to. This helps to counter potential claims by customers after they receive a bill for additional weight shipped versus the booking.
Once the station is ready to start weighing, ensure that this station is switched on in KLM systems as ‘certified’. This enables them to update the FWB with actual weight data.
Ensure that, after weighing, the GHA updates the FWB’ with the actual weights.
Actions
Start informing the GHA early on in the process about the weighing requirement. This way, they are able to purchase scales if they don’t have these already, and start the actual weighing process in week 5.
Some stations may already weigh 100% of cargo, other stations only a percentage of all cargo, and yet other stations may not conduct weighing at all. All will have to move towards 100% weighing

## Slide 19: Detailed roll-out plan 3.3 Compliance Checker
Implement the compliance checker, a software tool that checks the Air Waybills and verifies whether they meet the criteria set by customs authorities (e.g. PO box, address formats, commodities)
Login to the compliance checker via a regular internet browser: https://cbp-checker.digitalcargolabs.nl/. Username: cgn_user1 Password: 6uMf9^^#vc
Before FOH, view the compliance checker and scan for any irregularities
Within boundaries, adapt the FWB and FHL in case of irregularities, charge AWC (other charge)
Beyond boundaries, contact CSO to receive revised documents, before proceeding with RCS. If this is after truck departure, the shipment remains as FOH until new documents and a booking are available.
The URL does not work properly in Internet Explorer, use Chrome or Firefox
This is a new tool, and therefore a learning experience: We are looking for feedback from customers and GHA’s on the performance of the tool, so that we can make further improvements
Ultimately, we are seeking to integrate the compliance checker into the GHA’s own systems
3.3 Compliance Checker
What and why?
Actions

## Slide 20: Detailed roll-out plan 4.1 Assess and modify local contract/SLA
Review the existing local contracts and SLA’s with GHA’s and truckers to identify whether these require changes for EGFL and, if so, implement these changes before Go-Live
4.1 Review local contract/SLA
SLA
What and why?
Review the GHA contract and contact Willem van Roozendaal (Procurement) if changes are necessary. Focus specifically on the weighing procedures, requirement to send deviation reports, Go-Show reports and LAT reports, opening hours, feasibility of the contracted LAT (in minutes before DEP) and the acceptance processes described. Changing the contract is not always necessary.
Actions
Ensure that relevant contract changes if required are made at least 2 weeks before the scheduled Go-Live, to ensure a smooth transition
2.1
Link to:

## Slide 21: Detailed roll-out plan 4.2 Engage CSO to review local conditions
Review the current local conditions for customers and (if necessary) ensure that these are updated in accordance with EGFL before the Go-Live
4.2 Review local conditions
LC
What and why?
Look up the local conditions of the station/region on the AFKL Cargo website and review whether they meet the EGFL requirements. This includes a described LAT of 180 minutes before DEP, the new acceptance policy and fees for No-show, Low-show, High-show, different cargo buildup (loose rather than pre-built) and cancellations. Ensure that changes are made to the conditions if these deviate from the future EGFL situation.
Actions
See FRA local conditions for reference:
https://www.afklcargo.com/WW/en/common/about_us/local_conditions.jsp
If the LAT offset is changed, this should also be changed in the Traxon system (via Michael Totdenhaupt)

## Slide 22: Detailed roll-out plan 4.3 Set up KPI structure and monitoring
Ensure that daily and weekly performance data are captured from the GHA and CargoIQ to enable performance tracking. Use this in your weekly report to the GHA, local AFKL and truckers
4.3 Set up KPI structure and monitor performance
What and why?
Establish daily reporting of CargoIQ milestones (LAT, RCS, DEP at station; ARR, RCF, DEP at AMS) together with Performance Management (Bram Snel and/or Arend Feenstra). This has also been done for FRA, should be in the same format. Ensure that CargoIQ settings for customers are adjusted in one go, as these changes need to be accepted one by one by customers.
With the GHA, establish daily reporting of in-depth data (FOH/LAT, RCS and DEP) – the ‘LAT report’. This includes, on an individual shipment level, AWB numbers, booking trucks, flight numbers, truck arrival times at FRA, FOH times, departure times, among other items. This helps to identify performance gaps and, for example, allows you to see how early all cargo is delivered at the GHA by customers.
Each week starting 1 week before Go-Live, create a weekly performance report to share with the GHA, local AFKL, CSO and truckers. Follow the template used during roll-out Wave 1, containing an ABCD, performance overview, (see Appendix).
Actions
Focus on actual Flown As Planned (FAP) as this is what customers care about and pay for, however RCF is where EGFL has a direct impact.
Be careful to not share sensitive data with competitors in your weekly reports (e.g. 2 truckers serving the same station). In such a case, make 2 separate reports.

## Slide 23: Detailed roll-out plan 5a. Ensure ongoing communication with local AFKL and Network Planning
Ensure high-intensity inward communication and alignment with local AFKL units and Network Planning throughout the entire implementation phase
5a. Ensure ongoing communication with local AFKL, Network Planning
What and why?
Before Go-Live: Discuss the new truck schedule with NP. Particularly in regards to changing truck numbers, truck times and any other planning information. This is necessary to allow for NP to verify whether the new schedule is actually workable, and for them to make the necessary system changes to be ready for Go-Live.
Before Go-Live, give an initial presentation to the local AFKL about the EGFL project, its success and the drivers thereof. Show the EGFL promotion video with Marcel de Nooijer. This can help improve local support.
Continuously align with local AFKL operations. This is to ensure that the roll-out approach does not conflict with local requirements.
Actions
Strongest focus of the communication effort is on the first weeks up to the Go-Live. From week 3 onwards, this turns more into monitoring and corrective action.
The requirement to inform the Hub operations is limited; the new schedule and system should only make their life easier
IN

## Slide 24: Detailed roll-out plan 5b. Ensure ongoing communication with customers, GHA and truckers
Ensure high-intensity outward communication and alignment with customers, the GHA and truckers throughout the entire implementation phase
4.3
Link to:
Together with CSO, launch a customer newsletter to inform customers about EGFL-related changes. This includes process changes (e.g. new LAT times, LAT ‘enforcement’), but you can also use this to explain the benefits of EGFL to customers to build support. Do not send this letter too far in advance (e.g. 2 weeks prior to launch). Team up with local AFKL for this.
Before Go-Live, give an initial presentation to the GHA about the FRA case, its success and the drivers thereof. Show the EGFL YouTube promotion video with Marcel de Nooijer. This can help improve local support.
After Go-Live, ensure you are present at the outstation weekly, until no longer necessary. Ensure that we keep well aligned with the GHA and that issues are escalated and resolved quickly.
Ensure solid performance monitoring after the initial 8 weeks to see whether implementation sticks. See 4.3.
Strongest focus of the communication effort is on the first weeks up to the Go-Live. From week 3 onwards, this turns more into physical presence at the GHA, monitoring and corrective action.
Swissport, Jan de Rijk and Kühne + Nagel are involved from the start as consortium partners. Other actors will require an even stronger communication and change effort.
As a general rule, relevant stakeholders should all be (thoroughly) informed before any process changes are implemented. Follow the communication triangle (see Appendix).
5b. Ensure ongoing communication with customers, GHA and truckers
What and why?
Actions
OUT

## Slide 25: Detailed roll-out plan (Swissport) Swissport stations have an accelerated rollout, with 4 weeks of preparation and setup, followed by a roll-out of another 4 weeks.
51
0
1
2
3
4
5
6
Make preparations to enable start of weighing in week 5
3.3 Compliance Checker
1.2 Implement new trucking schedule
3.2 Weighing
1.1 Review schedule
2.2 Implement new acceptance processes
3.1 Selective Loading Rules
4.3 Set up KPI structure and monitor performance
2.1 Assess current acceptance process
4.2 Review local conditions
4.1 Review local contract/SLA
5a. Ensure ongoing communication with local AFKL, Network Planning and RM
5b. Ensure ongoing communication with customers, GHA and Truckers
Week
Weekly presence at station
1. Set up
key parameters
Preparation and setup
GO-LIVE
Report-out
5. Communications
and change
Activity
2. Implement
core processes
4. Supporting
activities
3. Implement
‘add-on’ processes
Onboarding
meeting
Preparation (2 weeks)

## Slide 26
Appendix
Stakeholder overview

## Slide 27: Stakeholder list
Class
Manage closely
External
Manage closely
Internal
Manage closely
External
Manage closely
Internal
Manage closely
Internal
Manage closely
Internal
Manage closely
External
GHA’s
Network Planning (NP)
Truckers
Customer Service Organization (CSO)
Revenue Management
Local AFKL operations
Customers
(shipper/forwarder)
Stakeholder
Potential for resistance
Involvement
GHA’s carry out the main tasks related to accepting cargo from customers on behalf of KLM Cargo, and loading the trucks to be sent to the hubs (AMS/CDG)
Network Planning ensures that trucks are booked/cancelled relative to the truck schedule, and monitor the trucking process throughout Europe
The trucker plays a key role in EGFL. The cargo planning relies on the truckers to stick to the given transit times, so that capacity at the hub is used effectively.
CSO is responsible for all communications towards the customer, including (re)bookings, no/go show follow-up and the design of local conditions
Revenue management is responsible for authorizing (re)bookings through the use of RM software that determines whether certain freight is profitable or not
Responsible for coordinating all local operational activities at the GHA in specific regions. Can be consulted (together with FJ’s) when issues with GHA arise
Customers are required to deliver cargo to the GHA that matches the booking (weight, volume, timeliness, documentation), to enable a seamless shipment

## Slide 28: Stakeholder list
AFKL Cargo SteerCo
The SteerCo signs off on critical next steps or investment decisions
Manage closely
Internal
Procurement
In the EGFL context, Procurement must ensure that local contracts/SLA’s are adapted to suit the requirements of the EGFL programme to the greatest extent possible
Manage closely
Internal
Customs authorities
Customs authorities are involved in the Cargonaut platform, and require a steady flow of information to ensure that cargo meets quality and safety standards
Keep satisfied
External
Stakeholder
Class
Potential for resistance
Involvement
Operations Development (FJ)
Responsible for managing the interface with truckers, GHA and CSO. Important stakeholder, can be consulted when critical issues related to these parties arise
Manage closely
External
Topsector Logistiek
Partially funds EGFL through the NLIP, for which several workpackages were defined with distinct deliverables related to the Phase 1 and FRA POC
Minimal effort
External
Cargonaut
Cargonaut is a software platform that ensures information exchange between private and governmental (e.g. customs) players at Schiphol airport
Keep informed
External
Competitors
No strong involvement, aside from competitors potentially occupying floor space at the GHA’s
N/A
Minimal effort
External

## Slide 29: Stakeholder map
Low involvement
Internal
High
involvement
Project
GHA’s
Network Planning (NP)
Truckers
Customer Service Organization (CSO)
Revenue Management
Customs authorities
Customers
Local AFKL operations
Topsector Logistiek
Operations Development (FJ)
Cargonaut
AFKL Cargo SteerCo
Procurement
Competitors
External
= Potential for resistance

## Slide 30: Stakeholder communication strategy
    Elapsed Time throughout Change
Contact
(Message sent)
Awareness
(Message received)
Understanding
(Message understood)
Positive perception
(Testing)
Adoption
(The new rules)
Institutionalisation
(The rules)
Internalisation
(Our way)
–
+
Degree of Commitment
Buy-In stages
Informed
Understand
Accept
Support / Engagement
GHA’s
Network Planning (NP)
Truckers
Customer Service Organization (CSO)
Revenue Management
Customers
Local AFKL operations

## Slide 31
Appendix
Process descriptions

## Slide 32: RACI Roles and responsibilities for GHA operations
GHA operations
In case of RCS failure (unhappy flow): identify problem and report to CSO
GHA Staff Warehouse
Customs
Customer
GHA Staff Office
Process
Roles
CSO
NP
Accountable
Responsible
Consulted
Informed
I
R
A
C
A
Unload truck, issue FOH
GHA Supplier
Physical Ready for Carriage check
C
Documentation check and issue RCS
AFKL Systems
Load (follow selective loading rules) and seal truck
I
Prepare shipping documents (customs, T1, manifests)
I
After RCS: buildup cargo for transport and consult NP in case info misses
Send deviation report (to NP) and FFM (to CSO and NP)
I
A
R
I
I
Confirm DEP in Cargoal
I
I
Enter arrival & departure time of loading truck (AFKL trucker)
Related to individual shipments
Related to AFKL contracted trucker
A
R
A
R
A
R
A
R
A
R
A
R
A
R
A
R
A
R
I
C
I
I
I
I
I
4
1
2
3
7
6
5
8
9
10

## Slide 33: RACI Roles and responsibilities for CSO operations
CSO operations
4
Respond to irregularities and contact customer, notify on next steps
1
I
A
Process booking
AFKL Cargo Market Manager
2
Ensure shipment matches booking by proactively contacting the customer
3
I
I
Process irregularities on shipment level
6
Consult with customer on deviations and take action (rebooking)
5
Process deviation report from GHA
C
CSO Office
RM
GHA
Customer
Process
Roles
NP
AFKL Systems
A
R
A
R
A
R
A
R
A
R
A
R
C
C
C
C
C
I
Accountable
Responsible
Consulted
Informed
I
R
A
C

## Slide 34: RACI Roles and responsibilities for Trucking operations
Trucking operations
4
Load truck according to safety standards
R
Trucker Office
NP
GHA
Truck driver
Process
Roles
1
Customs
Document-ation
A
Receive and process trucking order as sent by AFKL NP
Trucking supplier
2
R
Dispatch truck to loading point
3
I
Report arrival
AFKL Systems
7
Drive to Hub and keep office + AFKL updated on journey progress
I
I
6
Report departure
5
I
R
Collect documents and depart
8
Report arrival at Hub
I
A
R
C
9
Visit Documentation to transfer documents
I
I
10
Unload after receiving confirmation from Documentation
I
C
A
R
A
R
A
R
A
R
A
R
I
I
A
A
I
I
A
R
A
R
Accountable
Responsible
Consulted
Informed
I
R
A
C

## Slide 35: RACI Roles and responsibilities for Network Planning
Network Planning
4
Monitor arrival at Hub
1
C
C
A
C
Monitor booking list
Director Cargo Control Center
2
C
I
Make truck orders/cancellations vs schedule
C
3
I
Process deviation reports and inform CSO
7
Clean up booking list, consult with GHA in case of issues
C
6
Update flight planner based on new trucking information
I
5
C
In case of arrival issues, contact the trucker for updates
NP
Flight Planner
Trucker
CSO
Process
Roles
GHA
AFKL System
Accountable
Responsible
Consulted
Informed
I
R
A
C
A
R
A
R
A
R
A
R
A
R
A
R
A
R

## Slide 36
Appendix
Contact list

## Slide 37: Contact list
Content | Contact | Unit | E-mail
Station coordination | Sanja Mravik Duncan Tol Marco van den Berg Kenneth Fong | Operations Development (FJ) | Sanja.mravik@klmcargo.com Duncan.Tol@klmcargo.com Marco-van-den.Berg@klmcargo.com Kenneth.Fong@klmcargo.com
Contracts / supplier issues | Willem van Roozendaal | Procurement | willem.roozendaal@klmcargo.com
Local conditions / bookings | Local CSO | CSO | local
IT systems | Fred Timmers / Wilbert Akkermans | EGFL Project Team | fred.timmers@klmcargo.com / wilbert.akkermans@klmcargo.com
Truck planning | Network Planners | Network Planning | SPLCP.1@klmcargo.com – Nordics and eastern Europe SPLCP.2@klmcargo.com – Germany SPLCP.3@klmcargo.com – Italy and Switzerland SPLCP.6@klmcargo.com – UK/IE and Benelux
Escalation | Simon Spoor | EGFL Project Team | simon.spoor@klmcargo.com

## Slide 38: Communication
Hub
(NP / RM)
Local AFKL
(ops / commercial)
Suppliers
(GHA / RFS)
Informs customers!
Ultimately responsible, therefore needs to be able to influence decision-making
Include and make adaptions to the local situation if these surface from the discussion with the ‘triangle’

## Slide 39
Appendix
Selective Loading Rules - explanation

## Slide 40: Selective Loading Rules
13
26
11
7
6
15
33
23
17
21
Incoming freight
Truck positions
On truck
CT
7
6
13
11
15
21
17
23
26
33
5-10
11-15
16-25
26+
Grouping of cargo on plates with similar connection times at the Hub.

## Slide 41
Appendix
Station maps

## Slide 42: Station map EU trucking stations AFKL
CDG
AMS
= EGFL station

## Slide 43: Station map EU trucking stations KL
CDG
AMS
= EGFL station

## Slide 44
Appendix
X-Show varieties

## Slide 45: Acceptance varieties
Late-show
No-show
Go-show
High-show
Shipment arrives after LAT, but before DEP
Shipment is not there at DEP
Shipment arrives without a booking
Shipment exceeds booked volume or weight
Early-show
Shipment arrives exceedingly early, taking up storage capacity

## Slide 46
Appendix
GHA Visit Manual and Checklist

## Slide 47
European Green Fast Lanes
GHA Go-Live Visit Manual

## Slide 48: Handleiding stationsbezoek
Aandachtspunten: waar let je op?
Wekelijks rapport
Communicatielijnen: wie vertelt wat aan wie, en wanneer?
GHA Information package

## Slide 49: GHA Go-Live Visit Aandachtspunten
Go-Live visit (~5 dagen)
Vooraf:
Vluchten regelen, hotel regelen, schoenen regelen, pasje regelen
Ga langs het NP blok verantwoordelijk voor jouw station om kennis te maken, noteer telefoonnummers.
Agenda maken voor stations bezoek
Communiceer aanwezigheid op station in de planner, geef vluchten en hotelboekingen door in schema (tab 2 in de Planner)
Tijdens:
Participeren in de operatie, eigenaarschap nemen van station. Eerste prioriteit is het tijdig vertrek van de truck. En géén RCS geven totdat vracht daadwerkelijk goed bevonden is.
Registreren wat er gebeurt: Hoe wordt vracht aangeleverd en geaccepteerd? Wat gebeurt er als vracht te laat is? Hoe worden trucks geregistreerd? Hoe is het contact met NP? Komen de bestelde trucks op tijd (palletized 1 uur vóór DEP, Loose 2 uur vóór DEP, zie ok CPWorkflow)? Wordt de FBL op tijd ontvangen (~5 uur vóór DEP)? Wordt de final planning op tijd ontvangen? Worden de FWB’s goed ontvangen vanuit de klanten via KLM (Klant  KLM  GHA)? Hoe gaat men om met versturen van berichten? Updaten FWB (FWB’)? Wordt er gewogen? Worden weegbonnen gemaakt en bewaard? Hoe? Maak notities.
Communiceren: Leg aan de mensen op de vloer bij de GHA uit waar we mee bezig zijn, en waarom (je kunt hier het GHA info pakketje voor gebruiken, zie DB). Gaat er iets niet volgens plan (truckers te laat, klanten te laat?)  escalatie naar FJ’s en zorgen dat er snel actie + resultaat komt. Overleg ook als interns onder elkaar / help elkaar.
Rapporteren: Dagelijks feedback naar Simon/Vincent over voortgang. Op welke punten moet het plan aangepast worden?
Plan maken: Maak met de GHA een plan voor de volgende stappen (per wanneer 100% wegen? Wat is er hiervoor nodig?)
Na:
Rapportage maken van bezoek o.b.v. wat je gezien hebt en je notities, gebruik template
Bijhouden voortgangstracker, met notities waar nodig. Markeer issues.

## Slide 50: Handleiding stationsbezoek
Aandachtspunten: waar let je op?
Wekelijks rapport
Communicatielijnen: wie vertelt wat aan wie, en wanneer?
GHA Information package

## Slide 51: STATION - ABCD
Status Stream | Overall process:* |  | 
Achievements |  |  | Benefits
Concerns |  |  | Do next

## Slide 52: GHA Go-Live Visit Daily report (1)
Late-Shows
1
No-Shows
2
Trucks arriving late
3
AWB # | Customer | Total KG’s
AWB # | Customer | Total KG’s
Truck number | Trucking company | # minutes late
Trucks departing late
4
Truck number | # minutes late | Cause

## Slide 53: GHA Go-Live Visit Daily report (2)
Is the RCS check and RCS messaging carried out correctly? How?
8
Are FWB’s received correctly from customers (via KLM)?
9
If applicable: Are weighing + FWB’ processes carried out correctly?
10
Yes / No
Yes / No
Yes / No
Are FBL’s received on time? If not, action taken to repair?
5
Final planning received from NP on time? If not, action taken to repair?
6
Have deviation reports been sent to NP? If not, why? Any repair action?
7
Yes / No
Yes / No
Yes / No

## Slide 54: GHA Go-Live Visit Daily report (3)
Other notes/remarks
11

## Slide 55: Handleiding stationsbezoek
Aandachtspunten: waar let je op?
Wekelijks rapport
Communicatielijnen: wie vertelt wat aan wie, en wanneer?
GHA Information package

## Slide 56: GHA Go-Live Visit Principles
The truck leaves on time
Late is late: customers must deliver cargo on time. Repair is possible, but should not endanger the timely departure of the truck. See Late-Show process.
If more than one truck is required given the volume, additional trucks are scheduled before the booking truck
Focus on timely messaging of FOH and RCS
RCS is only given after cargo is checked and approved. Late-Shows (beyond repair) and Go-Shows are not accepted (only get FOH), and require a new booking.
Apply selective loading of pallets by following the planning sent by Network Planning
100% of cargo is weighed, FWB is updated with new weights and store weighing receipts
Send deviation reports to Network Planning max. 1 hour after truck departure (following the template)
Send daily FAP reports to Network Planning (following the template)
Send overview of Go-Show shipments to CSO

## Slide 57: GHA Go-Live Visit Communicatielijnen – Late-Show

## Slide 58: GHA Go-Live Visit Communicatielijnen – No-Show

## Slide 59: GHA Go-Live Visit Communicatielijnen – Go-Show

## Slide 60: GHA Go-Live Visit Communicatielijnen – High-Show

## Slide 61: Handleiding stationsbezoek
Aandachtspunten: waar let je op?
Wekelijks rapport
Communicatielijnen: wie vertelt wat aan wie, en wanneer?
GHA Information package

## Slide 62: What are we doing?
European Green Fast Lane is an AF/KL project that aims to improve the quality of incoming cargo shipments out of Europe towards the Hubs (Schiphol and Charles de Gaulle)
Simplified trucking schedules
Clear acceptance rules
‘Too late’
‘Too much’
‘Incorrect’
Shipment status updates
Customs and compliance checker
As ‘Rubbish In = Rubbish Out’, we aimed to eliminate waste by redesigning the Acceptance process based on Lean principles such as ‘First Time Right’ and ‘Just In Time’

## Slide 63: Why are we doing it?
To raise overall supply chain quality levels
To increase the reliability of our product
To increase the load factors of our aircraft
To shorten transit times
To ensure faster and easier customs handling
To enable a ‘lean’ hub operation

## Slide 64: How are we doing it?
Partnerships to optimize total chain performance and increase FAP
Trucking schedule rationalised and evenly spread over the day
Latest Acceptance Time adjusted to capabilities of the GHA
Weighing increased to 100% and FWB’ implemented
Ready for Carriage checks formalized and RCS processes corrected
Compliance checks for FWB and FHL implemented
Reporting mechanisms set up as feedback to customers and GHA
The project started with an Operational Proof of Concept for KL only, on the (biggest and most complicated) tradelane FRA-AMS. The process was adapted step by step:
The rest of the EU stations will follow in a phased roll-out, starting May 2017

## Slide 65: What does this mean for you?
Bigger spread of delivery times that will significantly reduce queueing
Peak reduction in the delivery process to enable flight optimization rather than truck optimization
After RCS is given, AF/KL will commit to a promise that it can keep
High-Show will keep priority within tolerance levels; otherwise, priority will be lowered
Targeted feedback on LAT (No-show / Late-show) and FWB/FHL compliance errors
Late-show shipments are rebooked at first available capacity before cargo is further transported
High-show is accepted, but FWB is adjusted and the invoice will be based on actual weight

## Slide 66: What needs to be in place?
Ability to send FOH and RCS status messages to Cargoal when cargo is received and accepted, respectively
Ability to create and send an adjusted air waybill (FWB’) when adjustments need to be made after weighing
Enforce new acceptance process, including strict adherence to LAT and following the ‘silver rule’. See the new process
Adhere to the cargo plannings (selective loading rules) sent by AFKL Cargo Network Planning
Send deviation reports for each truck to AFKL Cargo Network Planning after truck departure. Use the template.
Send daily FAP reports to AFKL Cargo that specify No-Show, Go-Show, High-Show shipments. Use the template.
Approve the new trucking schedule and create awareness of the changed truck schedule
Ensure 100% weighing of cargo and ensure that the weighing receipts are kept
Have door management and forwarder arrival + departure time registration and reporting in place